## SafeCircle Project
🛡 SafeCircle Project Tracker
USCrimeCenters LLC · safecircle.chat · Updated: April 17, 2026
# | Topic | Idea / Notes | Date Entered | Date Completed | Status
1 | Namecheap Domain | Check into the app. Namecheap domain registrar — connect safecircle.chat via CNAME on Railway. | 2026-03-27 | 2026-04-01 | ✅ Done
2 | Investors | Seek investors in blocks of $10,000+. Use Claude to research all available ESRI data centers nationwide. Scale to home health nurses, delivery drivers, social workers. Research companies that may want a licensed version. | 2026-03-28 |  | 🔄 In Progress
3 | USCrimeCenters Logo | Get USCrimeCenters.com donations logo added to the app. | 2026-03-29 | 2026-03-30 | ✅ Done
4 | Cancel Vercel | Cancel web hosting at vercel.com. Migration to Railway complete. | 2026-03-29 | 2026-03-30 | ✅ Done
5 | Investor Outreach | After a few weeks of stability, seek investors. Target blocks of $10,000 or more. | 2026-03-29 |  | ⏳ Pending
6 | Demo Video | Watch YouTube video, narrate into email to myself, convert to Andrew voice-over. Produce using Clipchamp. Script written by Claude. Snagit walkthrough at youtu.be/Mwd0nktbu1I. | 2026-03-29 |  | ⏳ Pending
7 | Panic Button Tab | Tab 4: Large red panic button. Activates live camera, SOS alert, GPS, siren. Designed to deter attacker if triggered. | 2026-03-29 | 2026-04-05 | ✅ Done
8 | Sign-Up / Payment Form | Form fields: first name, last name, sex, DOB last 4, credit card. Tiers: 1 month, 6 months, 12 months (single and family). Auto-timeout/shutdown if payment lapses. Option to finance. Install app icons on payment. | 2026-03-29 |  | ⏳ Pending
9 | Disclaimers | Visible disclaimer at start of every session. User clicks button acknowledging data accuracy not guaranteed and releasing SafeCircle from liability. | 2026-03-29 | 2026-04-02 | ✅ Done
10 | Donation Buttons | PayPal, Venmo, and donation buttons added. PayPal hosted_button_id=59GEQMLVVE68S for USCRIMECENTERS LLC. | 2026-03-29 | 2026-04-03 | ✅ Done
11 | What Makes Us Better | Owner-only button allowing John to post a video, text, or email response directly in the app — live messaging feed only John can update. Public submit form + admin 5-tap shield unlock. Built April 18, 2026. | 2026-03-29 | 2026-04-18 | ✅ Done
12 | Crime Markers on Map | Show map with a color-coded UCR icon on every marker matching the entered address. All incidents load once from ESRI into allMarkers[]. Filter buttons call marker.addTo(map) or marker.remove() only — no re-query. | 2026-03-29 | 2026-04-10 | ✅ Done
13 | Mobile Accordion Fix | Notebook/accordion not visible on mobile. Needs responsive CSS fix for Tab 1 on small screens. | 2026-03-29 |  | 🔧 Bug
14 | ESRI Public Safety Module | Extract ESRI calls-for-service function for use in Bloodhound. Officer can pull up prior calls at an address within 2.5-mile radius with a few clicks. Benoit has successfully tested this. Priority feature. | 2026-03-29 |  | 🔄 In Progress
15 | Address Persistence | Fix address persistence — entered address should survive tab switches and page refreshes without re-entry. | 2026-04-10 |  | 🔧 Bug
16 | Assessor Lookup Tab | Add Shelby County Assessor property lookup tab — owner name, assessed value, parcel data. | 2026-04-10 |  | ⏳ Pending
17 | safecircle.chat Domain | Namecheap CNAME pointing to Railway. DNS propagation pending. Verify connection once propagated. | 2026-04-10 |  | 🔄 In Progress
18 | UI Color Polish | Finish UI color theme — CartoDB Voyager map tiles, UCR category color-coded markers, consistent tab styling. | 2026-04-10 |  | ⏳ Pending
19 | page.tsx Crash Fix | importCsv() function declaration stripped (Voice Access). Bare const statement caused fatal syntax error on startup. Fixed April 18, 2026. | 2026-04-18 | 2026-04-18 | ✅ Done
20 | Expand the Application | A large city like New Orleans, Chicago, or Denver — expand SafeCircle beyond Shelby County to additional metro ESRI data sources and warrant endpoints. | 2026-04-18 |  | ⏳ Pending